## Sheet1
City/Town | Area | State | Stop # | Arrival Date | Departure Date | Event(s) | Visit # Nights
Eureka | West Coast | CA | 1 |  | 2016-04-15 |  |  | Note: We expect to be able to leave in mid-April but possibly not in May, so we're pre-placing the boat early in the Astoria / Portland area.
Coos Bay | West Coast | OR | 6 | 2016-04-21 | 2016-04-30 |  | 9
Astoria | West Coast | OR |  | 2016-05-01 | 2016-05-15 |  | 14
Ellensburg, Yakima, Wenatchee, Spokane by car - presentations and invitations to other events | Eastern | WA/OR |  | 2016-06-01 | 2016-06-07 | Speaking tour by car | 6 | No boat here, going by car
Portland | Columbia River | WA/OR | 12 | 2016-05-15 | 2016-06-10 | June 8-12 Fleet Week (June 11 Rose Parade) Big Official Arrival on Saturday May 7 | 26
Hood River | Columbia River | WA/OR | 13 | 2016-06-12 | 2016-06-14 | stop overnight for shower if time allows | 2
Tri-Cities | Columbia River | WA/OR | 14 | 2016-06-16 | 2016-06-19 | "Official/Press" arrival on 17th | 3
Hood River | Columbia River | WA/OR | 13 | 2016-06-21 | 2016-06-22 |  | 1
Vancouver | West Coast | WA | 11.1 | 2016-06-24 | 2016-06-24 |  | 0
Seabeck | Key and Olympic Peninsulas | WA |  |  |  | July 1-4 FOR (Near Bangor). Approx 63 mi from Seabeck to Lk Union - SO best to have someone attend and give a presentation but not with the boat - the Festival of Wooden Boats is higher priority. Have the boat there right before the convention, maybe? |  | No boat here, going by car
Seattle - Lake Union | Lake Union | WA | 16.5 | 2016-07-01 | 2016-07-05 | July 2-4 Festival of Wooden Boats, Lake Union | 4
Mercer Island, Bellevue, Redmond, Renton | Lake Washington | WA | 38 | 2016-07-05 | 2016-07-18 |  | 13
Tacoma | S. Puget Sound | WA | 32 | 2016-07-18 | 2016-07-20 |  | 2
Olympia | S. Puget Sound | WA | 30 | 2016-07-22 | 2016-07-25 | Glen Anderson in Olympia | 3
Shelton | S. Puget Sound | WA | 29 | 2016-07-25 | 2016-07-28 |  | 3
Gig Harbor | S. Puget Sound | WA | 31 | 2016-07-28 | 2016-07-30 |  | 2
Seattle - Elliott Bay | Puget Sound | WA | 36 | 2016-08-01 | 2016-08-08 | August 3 - 7 Fleet Week, Guest dock at Pier 66 Bell Harbor Marina, war ship tours Th - Sunday | 7
Greenlake Lantern Ceremony | Puget Sound | WA |  |  |  | August 6 Lantern Ceremony Greenlake - table |  | No boat here, going by car
Ground Zero / Bangor / Bremerton, Silverdale, Keyport, Poulsbo, Kingston | N. Puget Sound | WA | 37 | 2016-08-12 | 2016-08-15 | August 12-14 Buzz Bangor , August 7-8 Hiroshima / Nagasaki Commemoration at GZ Center. 7th is planning the action, 8th in the morning is the action itself. Therefore, the following weekend makes sense for "Buzz Bangor", Mary Glysteen - has a dock at Kingston | 3
Everett - Naval Station | N. Puget Sound | WA |  |  |  | August 18 Evict Everett Naval Station
Anacortes / Whidbey Island Naval Air Station | N. Puget Sound | WA |  | 2016-08-16 | 2016-08-22 | August 17 Whip Whidbey Naval Air Station | 6
Bellingham, Lummi climate activists | N. Puget Sound | WA | 28 | 2016-08-23 | 2016-08-28 |  | 5
Vancouver, BC | Canada | CAN | 27 | 2016-08-29 | 2016-09-02 |  | 4
Victoria | Canada | CAN | 26 | 2016-09-03 | 2016-09-06 |  | 3
Friday Harbor | Key and Olympic Peninsulas | WA | 29 | 2016-09-07 | 2016-09-08 |  | 1
Pt. Townsend | N. Puget Sound | WA | 44 | 2016-09-08 | 2016-09-12 | Sept 9 - 11 Wooden Boat Festival | 4
Port Angeles | Key and Olympic Peninsulas | WA | 25 | 2016-09-13 | 2016-09-16 |  | 3
Neah Bay | West Coast | WA | 24 | 2016-09-17 | 2016-09-19 |  | 2
La Push | West Coast | WA | 23 | 2016-09-20 | 2016-09-22 |  | 2
Gray's Harbor / Aberdeen / West Port / Ocean Shores | West Coast | WA |  | 2016-09-23 | 2016-09-26 |  | 3
Willapah Bay | West Coast | WA |  | 2016-09-27 | 2016-09-29 |  | 2
Astoria | West Coast | OR |  | 2016-09-30 | 2016-10-02 |  | 2
Seaside | West Coast | OR | 11 | 2016-10-02 | 2016-10-03 |  | 1
Nehalem | West Coast | OR |  | 2016-10-03 | 2016-10-04 |  | 1
Tillamook | West Coast | OR | 10 | 2016-10-04 | 2016-10-05 |  | 1
Lincoln City | West Coast | CA | 3 | 2016-10-06 | 2016-10-07 |  | 1
Newport | West Coast | OR | 8 | 2016-10-08 | 2016-10-09 |  | 1
Waldport | West Coast | OR |  | 2016-10-10 | 2016-10-11 |  | 1
Yachats | West Coast | OR |  | 2016-10-11 | 2016-10-11 |  | 0
Reedsport / Winchester Bay | West Coast | OR |  | 2016-10-11 | 2016-10-12 |  | 1
Crescent City | West Coast | CA | 4 | 2016-10-13 | 2016-10-15 |  | 2
Eureka | West Coast | OR | 5 | 2016-10-15
Navigating the Columbia River Chart Links to NOAA |  | http://www.walleyewarriors.com/component/content/article/1-latest/87-columbia-river-levels